## Slide 1: Undergoing Digital Transformation in Public Health
amidst a Pandemic

## Slide 2: Today’s Discussion is around our EHR Implementation
Well Done?
Missed Opportunities?

## Slide 3: What we did well
Created Team as Expert with the right RR&Es
Adjusted to the daily changes of major tasks affecting deliverables
Thought outside the box on vendor dependent tasks
Implemented multiple leveraged business applications to assist

## Slide 4: RR&E (Role, Responsibilities and Expectations) = EHR Implementation Team
Implementation Leader
Implementation Support Analyst
Data Specialist
2 Application Specialist
Project Manager
Training Coordinator
Process and Workflow Coordinator

## Slide 5: Responding to Rapid Changes
Dependencies:
News stories and media perceptions
Perceptions of Sedgwick County citizens
Perception of County Managers and Public Health Leaders
Adoption of the Workforce

## Slide 6: Thinking outside the box
Hosted the “Make the Connection” Hackathon with EHR Vendor and KDHE

## Slide 7: Other Digital Transformations
Other Implementations include
Monday.com
Implemented the QLess application to assist with
Consumer Scheduling plugin to EHR
Vaccine Inventory System (Accuvax)

## Slide 8: Lessons Learned
Clarity
Leadership
Criticality
Stakeholder Engagement

## Slide 9: Abandoned…until further notice

## Slide 10: Leadership leave meetings without having consulted I.T.
…and the entire meeting was about installing a process or solution that has everything to do with I.T.

## Slide 11: Critical Missed Opportunity = Athena and Billing
Assumptions about automated billing
What are the gaps?
What do staff need to know?

## Slide 12: Exit Criteria and Accountability from a board of representatives

## Slide 13: Thank you so much
All the best,
Sonya V. Norris, public health systems analyst